## Sheet1
| FORM NO. VPR0039 |  | DATE : 06-01-2026
VEHICLE PURCHASE
Sr. | Heading | Description | Responsibility | Plan Date | Complete date | review date | Status
1 | Seller Name | ANILKUMAR ARJUNDAS | Mohit |  |  |  | OK
2 | Vehicle Number | GJ32GB5192 | Mohit |  |  |  | OK | pending
3 | Model | LPS4018TC/32 | Mohit |  |  |  | OK | running
4 | Month & Year of Manufacturing | 2016-03-01 | Mohit |  |  |  | OK | finished
5 | Date of Registration | 2016-04-12 | Mohit |  |  |  | OK
6 | Engine No. | B591803261C63504299 | Mohit |  |  |  | OK
7 | Chassis No. | MAT447220G1C07205 | Mohit |  |  |  | OK
8 | Registering Authority | KOTPUTALI , RAJASTHAN | Mohit |  |  |  | OK
9 | Price Horse | 1160000 | Mohit |  |  |  | OK
10 | Price Tyres | 0 | Mohit |  |  |  | OK
11 | Verify RC | Verified | Mohit |  |  |  | OK
12 | Fitness Date | 2025-12-19 | Mohit |  |  |  | OK
13 | Insurance Date | 2025-12-17 | Mohit |  |  |  | OK
14 | PUC Date | 2026-01-25 | Mohit |  |  |  | OK
15 | TAX Date | 2025-03-31 | Mohit |  |  |  | OK
16 | Permit Date | 2026-12-20 | Mohit |  |  |  | OK
17 | National Permit Date | 2025-12-20 | Mohit |  |  |  | OK
18 | HP | No | Mohit |  |  |  | OK
19 | RTO Challan pending | No | Mohit |  |  |  | OK
20 | Advance payment | 100000 - 6/1/26+400000 31/1/26 + 160000 12/2/26 | Chirag |  |  | multipal payment make option | OK
21 | RTO NOC |  | Mohit | 2026-01-29 |  |  | OK
22 | Sign sale agreement |  | Chirag | 2026-02-18
23 | Make Full Payment |  | Chirag | 2026-02-18
24 | Schedule pickup, take delivery with delivery note and original documents. |  | Mohit | 2026-02-18
26 | RTO Process Start Date |  | Libin | 2026-02-23
27 | Modification Start Date | Not Applicable
28 | Modification End Date | Not Applicable
29 | RTO Complete Dt |  | Libin | 2026-03-23
30 | Insurance Name Change Dt |  | Dasak | 2026-03-27
30 | Number Plate Generate |  | Libin | 2026-03-30
31 | On Road |  | Libin | 2026-04-01